## Arkusz1
* |  | Oct 2016 |  |  |  | Nov 2016 |  |  |  | Dec 2016 |  |  |  | Jan 2017 |  |  |  | Feb 2017 |  |  |  | Mar 2017 |  |  |  | April 2017
|  | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4 | week 1 | week 2 | week 3 | week 4
Project Planning |  | 3 | 2 | 4 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| this plan | Oct 2016 week 4: 2
| write aim, objectives | Oct 2016 week 1: 3
| produce project outline | Oct 2016 week 2: 2
| project requirement specs. | Oct 2016 week 3: 4
compare this plan vs. reality | bar: Oct 2016 week 4; Nov 2016 week 4
Background Research |  | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Techniques used to achive aims | bar: Nov 2016 week 1; Nov 2016 week 3
| Game Client Packet Structures | Nov 2016 week 2: 3
| Massive character Creation | Nov 2016 week 1: 2
| Game Server inftrastucture | Nov 2016 week 3: 2
| Anti cheat system | Nov 2016 week 3: 4
IP, port discovering | bar: Nov 2016 week 2
| Already existing cheats | Nov 2016 week 4: 3
| Legal, Social, Ethical and Private Issues | Nov 2016 week 4: 2
DLL Injection | bar: Nov 2016 week 4
Proxyfying | bar: Nov 2016 week 4
Lua Scripting Lenguage | bar: Nov 2016 week 4
Milestones & Assessments |  | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1st Presentation & preparation
| Project Requ. Definitions | Nov 2016 week 1: 2
Mid Term Assessment
Design Docs & Test/Eval. Plan
Report & 2nd Presentation
Implementation |  | 0 | 0 | 0 | 0 | 2 | 12 | 12 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design
| Massive character creation | Nov 2016 week 1: 2
| Massive charactet login | Nov 2016 week 2: 12; Nov 2016 week 3: 12; Dec 2016 week 1: 10
DLL Injection code
DLL
Reverse Engineering
Proxy
Experimental Features
Documentation
Testing & Evaluation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
write test plan
implement unit tests | bar: Nov 2016 week 1
debugging
write evaluation documentation
user evaluation
implement modifications
Writing Up |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 6 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Notes | Nov 2016 week 3: 1; Nov 2016 week 4: 3
| Almost-usable documents | Nov 2016 week 2: 2; Nov 2016 week 4: 3
| Chapters | Dec 2016 week 1: 6
| Milestone | Dec 2016 week 1: 10
Final work
Other Commitements |  | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Exam Preparations
| Assignments | Nov 2016 week 3: 8; Nov 2016 week 4: 20; Dec 2016 week 1: 12
Social
Other-Other
Total |  | 3 | 2 | 4 | 3 | 8 | 18 | 28 | 35 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total excluding other commitments |  | 3 | 2 | 4 | 3 | 8 | 18 | 20 | 15 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0